## Ark3
SEMESTER PROJECT |  |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4
|  |  | Date | 2020-02-03 | 2020-02-04 | 2020-02-05 | 2020-02-06 | 2020-02-07 | 2020-02-08 | 2020-02-09 | 2020-02-10 | 2020-02-11 | 2020-02-12 | 2020-02-13 | 2020-02-14 | 2020-02-15 | 2020-02-16 | 2020-02-17 | 2020-02-18 | 2020-02-19 | 2020-02-20 | 2020-02-21 | 2020-02-22 | 2020-02-23 | 2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-02-29 | 2020-03-01
Student: Tom Stian Fjermeros |  |  | Days | 2020-02-03 | 2020-02-04 | 2020-02-05 | 2020-02-06 | 2020-02-07 | 2020-02-08 | 2020-02-09 | 2020-02-10 | 2020-02-11 | 2020-02-12 | 2020-02-13 | 2020-02-14 | 2020-02-15 | 2020-02-16 | 2020-02-17 | 2020-02-18 | 2020-02-19 | 2020-02-20 | 2020-02-21 | 2020-02-22 | 2020-02-23 | 2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-02-29 | 2020-03-01
TASKS | START DATE | END DATE
Gantt Cart | 2020-02-03 | 2020-02-04
Gantt Cart Delivery | 2020-02-09 | 2020-02-09
Research | 2020-02-05 | 2020-02-05
Design | 2020-02-04 | 2020-02-16
Sketches | 2020-02-06 | 2020-02-07
Graphic Design | 2020-02-07 | 2020-02-16
HTML/CSS
Mobile Devices | 2020-02-17 | 2020-02-21
Laptop Devices | 2020-02-21 | 2020-02-25
Test | 2020-02-23 | 2020-02-28
Report | 2020-02-29 | 2020-02-29
Delivery Day | 30.02.2020 | 30.02.2020
Resarch: look around for inspirasion for my web page
Sketches: Playing around whit different layout for the web and mobile devices, colors and use of pictures
Graphic Design: Make tamplets, color design and how the page will look
HTML/CSS: Starting dveloping the website and get it functional for laptop and mobile devices and test the website
I used "Recomended process" to get som inspiration to set up my Gantt chart. This is a very good way to plan may days for the next week.
I don't know if this wass what you ment whit "supporting text" but this is how i understande it.
Formulas:
Week 1 = [Week 1, row above]
Week 3 = [Week 3, row above]